## Gantt Chart
Project Name
TEAM NAME
START DATE |  | 2024-04-29
END DATE
PROJECT MANAGER |  | Ng. A
MEMBER LIST |  | Ng. B
Ng. C
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
[6 empty] | TODAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105
1 | Project Conception and Initiation | time axis 2024-04-29 to 2024-08-11
1.1 | Chọn đề tài để bắt đầu dự án | Như | 2024-05-11 | 2024-05-11 | 0 | 100%
1.2 | Thiết kế cấu trúc thư mục dự án | Trung | 2024-05-11 | 2024-05-18 | 7 | 100%
1.3 | Chọn IDE VScode để phát triển dự án | Như | 2024-05-11 | 2024-05-11 | 0 | 100%
1.4 | Chọn RDBMS SQLite để lưu trữ và phân quyền dự án | Trung | 2024-05-18 | 2024-05-18 | 0 | 100%
1.5 | Chọn Github để lưu trữ mã nguồn | Như | 2024-05-19 | 2024-05-19 | 0 | 100%
1.6 | Chọn Git để quản lý các phiên bản của dự án | Trung | 2024-05-19 | 2024-05-19 | 0 | 100%
1.7 | Chọn công cụ Gradle để quản lý dự án | Trung | 2024-05-20 | 2024-05-20 | 0 | 100%
1.8 | Chọn công cụ Selenium IDE và NUnitTest C# để kiểm tử phầm mềm | Trung | 2024-05-24 | 2024-05-24 | 0 | 100%
2 | Project Definition and Planning
2.1 | Viết README hướng dẫn tham gia dự án | Như, Trung | 2024-05-17 | 2024-07-10 | 53 | 10%
2.2 | Cài đặt công cụ gradle | Trung | 2024-05-20 | 2024-05-21 | 1 | 80%
2.3 | Thiết kế và Cài đặt cơ sở dữ liệu | Trung | 2024-05-22 | 2024-05-24 | 2 | 70%
2.4 | Tạo các phương thức CRUD để quản lý Database |  | 2024-05-25 | 2024-06-01 | 6 | 0%
2.5 | Tạo các lớp Model ( OOP ) để tương tác với CSDL |  | 2024-05-25 | 2024-06-01 | 6 | 0%
2.6 | Tạo các lớp Controller để xử lý các logic nghiệp vụ và thực hiện CRUD |  | 2024-05-25 | 2024-06-01 | 6 | 0%
2.7 | Xây dựng các phương thức trong Controller |  | 2024-06-02 | 2024-06-08 | 6 | 0%
2.8 | Thiết lập TCP server để giao tiếp với client và ngược lại (sử dụng ServerSocket để giao tiép) |  | 2024-06-02 | 2024-06-08 | 6 | 0%
2.9 | Tích hợp TCP với controller để xử lý yêu cầu từ client |  | 2024-06-09 | 2024-06-15 | 6 | 0%
2.1 | Xây dựng Giao diện người dùng |  | 2024-05-25 | 2024-06-04 | 9 | 0%
2.2 | Xây dựng các chức năng của người dùng (vd: đăng nhập, đăng ký bằng OTP,..v.v) |  | 2024-06-05 | 2024-06-15 | 10 | 0%
2.3 | Kết nối giao diện tới TCPclient để xử lí và truyền tải đến server |  | 2024-06-16 | 2024-06-22 | 6 | 0%
2.4 | Xây dựng các chức năng HTTP file và ảnh trong controller, sử dụng TCP để truyền tải data từ client xuống server |  | 2024-06-16 | 2024-06-29 | 13 | 0%
2.4 | Test các chức năng trong các module đã cài đặt |  | 2024-06-30 | 2024-07-10 | 10 | 0%
3 | Coding
3.1 | Database Tables | Trung | 2024-05-22 | 2024-05-23 | 1 | 0%
3.2 | CRUD user, Model User, UserController | Trung | 2024-05-24 | 2024-05-25 | 1 | 0%
3.3 | CRUD files, Model Files, FilesController | Trung | 2024-05-25 | 2024-05-26 | 1 | 0%
3.4 | CRUD folder, Model folder, FolderController | Trung | 2024-05-25 | 2024-05-26 | 1 | 0%
3.5 | CRUD images, Model images, ImagesController | Trung | 2024-05-25 | 2024-05-26 | 1 | 0%
3.6 |  |  |  |  | 0 | 0%
3.7 |  |  |  |  | 0 | 0%
3.8 |  |  |  |  | 0 | 0%
3.9 |  |  |  |  | 0 | 0%
[5 empty] | 0 | 0%
4 | Testing
4.1 | MH Dang ky | Ng. C | 2024-05-17 | 2024-05-17 | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%
4.6 |  |  |  |  | 0 | 0%
4.5 |  |  |  |  | 0 | 0%
4.7 |  |  |  |  | 0 | 0%
4.8 |  |  |  |  | 0 | 0%
[5 empty] | 0 | 0%
5 | Deploy
5.1 |  |  |  |  | 0 | 0%
5.2 |  |  |  |  | 0 | 0%
5.3 |  |  |  |  | 0 | 0%
5.4 |  |  |  |  | 0 | 0%

## FixRequest
FixRequest
No. | ステージ Stage | 名前 Name | 記入日 Date | 指摘内容 Contents | スクリーンショット Screenshot | URL / 画面名 URL / Screen name | Case ID. *Required | 対応ステータス Status | 担当者 P.I.C | 担当者コメント P.I.C Comment | 対応完了日 Finish date
| Dev | Trung | 2024-05-20 | Gradle : Build failed with an exception : Execution failed for task server:compileJava > Could not find org.apache.commons:commons-net:3.10.0 |  |  |  | Done | Trung | Đổi thư viện Commons-net thành thư viện Apache Mina SSHD | 2024-05-21
2 | Dev | Trung | 2024-05-21 | :err :unmappable charater (0x90) for encoding window-1252 |  |  |  | Done |  | Cấu hình gradle để sử dụng UTF-8 khi compile Java | 2024-05-21
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17

## .setting (hidden)
QA status | FixRequest status | Stage
New | New | Dev
Answered | Doing | Stage
Closed | Fixed | Production
Re-Confirm | Done
Pending
Waiting